FOOD GRAINS PROJECT

1. Fill Registration Form by the middle of February.

Forms are sent out to us. Herbicide requests are

In the registration form.

 2)Arrange for seed from CPS in early March.

 3)Arrange for fertilizer at Paragon Ag. Services in March.

4)Talk to Reagen at Cervus to confirm seeding plans in March.

 5) If requests for herbicide don’t come through arrange for other options.

 6) Make arrangements for a truck to haul fertilizer and seed.

 7 Keep in contact with Reagan with regards to seeding and spraying.

 8) Contact AK Ens Trucking in August regarding trucking.

 9) Contact Randy Penner at Viterra to confirm delivery of crop.

 10) Keep in contact with Reagan regarding swathing, desiccating and combining.

 11) Arrange with Rotary to have lunch in the field when harvesting.

 12) Talk to Reagan and Paragon about putting on NH3 in the fall if possible.

 13) Ask Reagan to invoice us for fuel and then give it to PNC to pay.

 14) Get hold of Rick Block from Food Grains to arrange a time for him to speak.

 Invite all the sponsors to attend the meeting as well.

 15) Talk to Reagan before the end of the year to confirm that he will do it the

 next year.