Chairman: Sara Holland

- Arranges for hall rental and determines date and time of the event.

- Reviews and publishes a job description for each Committee Chair.

- Publishes a timeline for completion of tasks.

- Appoints Committee Chairs and assigns persons to each committee.

- Review job description of each chair to coordinate activities and ensure that each chair has understanding and resources to complete his/her tasks.

- Creates an event budget, and reviews needs with committee chairs.

- Readjusts job assignments as necessary.

- Reports to Club on progress and results of the event.

Marketing Chairman: Kathy Kearns

- Assists Chairman with duties as requested.

- Designs, budgets for, and implements, all marketing efforts for both the event and grand prize ticket sales to include:

  - Notifying local chambers of commerce, PBCAM, Record Enterprise, Laconia Citizen, Union Leader and others to include in their personal e-mails and/or websites.

  - Distributing PDF file of Event to all members to include in their personal e-mails and/or websites.

  - Distributing 200 posters.

  - Arranging radio PSAs or complimentary ads.

  - Arranging Banners to be hung at various locations, including: Hannaford's two exits, Chestnut Hill Mobile home sales and roundabout on Main Street.

  - Soliciting others to assist as required.

- Arranges for music for evening or DJ.

- Works with the Grand Prize Chair to coordinate promotional efforts.

- Contacts each school in the SAU and SAU Office to distribute Penny Sale Flier and information to parents.

- Coordinates radio and news spots.

Prize Chair: Steve Rand/Paul Brochu

- Reviews list of previous prize donors, adds and deletes from the list, and creates prize solicitation assignment list for each club member.

- Trains new and old members in techniques and objectives of prize collection.

- Reminds members of approaching deadlines.

- Provides Contribution acknowledgement letters to solicitors.

- Provides Gift Identification Forms to members and instructs them on proper use.

- Follows up on all prizes not delivered by set-up night.

- Creates list of prizes during prize assembly night and ensures that prize lists are complete and available for night of the Penny Sale. Creates cross-referenced item list to sheet color and number by Rotarian solicitor.

- Secures raffle tickets for floor sales.

- Check operation and arrange delivery of ticket drum

- Reminds members of importance of acknowledging gifts in writing.

Grand Prize Chair: Ken Evans

- Selects Grand Prize(s) and arranges for purchase or donation of same.

- Coordinates with Marketing Chairman to create a marketing program for grand prize ticket sales.

- Prints 6,000 tickets (unnumbered, plenty of space for writing) and determines price structure for tickets.

- Provides periodic sales progress reports to Club.

- Maintains records of all ticket sales and return receipts with accounting to the Bank Chair.

- Takes special efforts to thank Grand Prize sponsors for their support.

Ticket Sales Coordination Sub Committee: Joan Randlett

- Determines dates and venues for booth ticket sales and assign each member to duty.

- Sets up tables, a sign, money drawers for ticket sales and sweeps proceeds on a periodic basis, making sure that change is available.

- Distributes 100 tickets to each member as their personal sales obligation and train on techniques of selling.

- Tickets and Cash Boxes located in Steve Rand’s Office. After your shift please put all the ticket stubs Sold and Cash collected in an envelope with your name, date, location, # of ticket stubs and cash collected on the envelope.

Penny Sale Event Ticket Sales Sub Committee: Cheryl

- Sells grand prize tickets at Penny Sale

- Coordinates drawing and announcement of winners and distribution of prizes.

- Coordinates and staffs a money-changing booth at the same table.

- Provides a supply of clipboards for grand prize ticket buyers.

Gym and Prize Setup Chair:   Bill Clark/Peggy

- Coordinates with High School Staff to secure space for prize set-up night on the Weds. 10 Days before the Penny Sale and for storage of items.

- Oversees prize set-up to ensure that all items are tagged, properly described and secured.

- Arranges for tarp on gym floor, tables (5 large for each prize list, 1 for ticket drum, 2 for Grand Prize, 1 for sheet distribution, 2 for food concession), chairs and arranges for microphone for the night of the event.

- Sets up display of prize items starting at 3:00 day of Penny Sale

- Brings Rotary banner, Rotary Name badges and sets them up.

- Oversees final cleanup of building before leaving on the evening of the Penny Sale.

Floor Sales and Prize Distr. Chair: Mike Cameron

- Secures commitment from Members and assigns manpower for:

  - Prize sheet distribution to attendees

  - Floor Sales

  - Pickup and tearing of sold tickets

  - Prize Distribution

- Ensures that members arrive at event early (at least 2 hours before event)

- Assign committee members to specific jobs and areas of the gym.

- Ensures that committee members are trained to do each job and that they shift job responsibilities at appropriate times, if multi-tasked.

Subcommittee:  Auxiliary Help Chair: Gail

- Arranges for help from outside groups or individuals in conducting the Penny Sale and ancillary events (Boy Scouts, Rotarian Children, PRHS Honor Society, etc.).

- Determines needs of various committees and acts as liaison to assign and train volunteers for their duties.

Bank Chair: Martha Hughes

- Receives all income from the Penny Sale from all sources and accounts for the same.

- Obtains change for the event including cash for food concession, games of chance and for a floor change booth.  Runs bank for ticket sales.  Arrives by 5:30 on Penny Sale night to ensure proper set-up of all cash needs.

- Delivers all receipts to club treasurer and reports to Chair.

Announcers:   Tim

- Rotate announcement responsibilities

- Understand and communicate Penny Sale rules and procedures to the crowd.

- Reinforces CHARITY nature of event and uses of proceeds.

- Announce special events and happenings, food concession, games of chance, etc.

- Keep it moving, fun and entertaining.

- Acknowledge special contributions.

Food Concession Chair: Sharon

- Arrange for food to be provided by PRHS Culinary Arts Program.

(Will John Spear and PRHS provide all supplies with all profits going to Rotary?  If not, see below. )

- Purchase food supplies, arrange for necessary equipment and provide manpower for a food concession in hallway outside main hall.

- Determine pricing and provide necessary signs.  Get change from bank chair and return proceeds to him.

- Keep records of food sold and opportunities lost for future years.

- Clean area after use.

Games of Chance Chair: Ben Amsden

- Determine what games to conduct, arrange for delivery and set-up of equipment, and manpower for games of chance for children and for other side activities in the outside hallway.

- Keep records of proceeds for future analysis.

- Get change from Bank Chair and return all proceeds to him.

Turkey Detail Chair:  Peggy Smith

- Arranges for donation/purchase of turkey certificates.

- Coordinates with Announcers for add-in of Turkey awards.