ASAP

- Chair sets date of Penny Sale

- Chair reserves the Plymouth Regional High School gym for that date and for setup 2 Wednesdays prior to event.

- Chair names Grand Prize Chair and sets deadline for finalizing grand prizes for first Wednesday in September.

9/6/2017 Wednesday - Morning Meeting

- Grand Prizes Finalized

- Chair distributes:

  - Job Assignments

  - Job Descriptions

  - Time Lines

  - Solicitation Assignments

9/13/2017 Wednesday – Morning Meeting

- Chair distributes Grand Prize Tickets to all members

- Finalize and distribute assignments for Grand Prize Ticket Sales

- Distribute Item Tag Sheet to all members

- Locate all Penny Sale property:

  - Banners

  - Tickets

  - Drum

  - Accessories

9/28/2017 Wednesday – Morning Meeting

- Posters to members for distribution

9/30/2017 Through 11/3/2017

- Sidewalk Grand Prize Ticket Sales per schedule

- Online Grand Prize Ticket Sales, via webpage and FB

10/17/2017

- Press release to Evening Citizen, Union Leader

- Put up Banners and Tent Signs

10/18/2017 Plymouth Regional High School 5pm

- Deadline for Prizes

- Assemble Prizes at High School

10/19/2017

- Penny Saver Ad Deadline for 10/25 Issue

- Record Enterprise Article Deadline for 10/24 Issue

10/26/2017

- Record Enterprise Ad Deadline for 11/1 Issue

11/4/2017 Plymouth Regional High School

- Last Call for Unplaced Gifts

- Setup Committee arrives at HS at 3:30pm with unplaced gifts

- All members at HS at 5:30pm

- Penny Sale Doors Open at 7pm