## Slide 1: Strategic Initiatives for our Club for the next 3 - 4 years
The Journey so far
Opinion Survey – Oct-Dec 2022
Visioning Day Activities – Mar1, 2023
Refining to Concrete Goals/Initiatives – April, 2023
Board Approval – April 2023
With help from Kathy Y, Steve O and Alysa S

## Slide 2: The Crystalized Goals/Objectives/Initiatives
Adoption and Work on at least two active BHAGS (Big, Hairy, Audacious Goals)
1. Mary Avenue Project (In-Process)
  Scope out the opportunities to participate actively in and costs for funding a community room perhaps in the Mary Ave project in 2023-2024 and following years engage with the community to do hands on projects and get their involvement
2. Climate BHAG and/or Food Security BHAG:
  Within the next year, research, develop, propose and adopt a second BHAG that will be a “statement” project in the area of climate action or food security

## Slide 3: The Crystalized Goals/Objectives/ Initiatives
ACTIVATE DIVERSE PARTNERSHIPS TO AMPLIFY OUR IMPACT (ACTIVATE TO AMPLIFY): Work with at least 2 new partners
As a club we can expand our impact by consciously reaching out to form and activate partnerships with other organizations to leverage and broaden network of relationships
During RY 23/24, identify and collaborate with at least 2 new partners in accomplishing a significant project.
During RY 24/25, review the impact of partnership outreach in prior year expand by another 2 new partners.

## Slide 4: The Crystalized Goals/Objectives/Initiatives
PROMOTE OUR WORK AND COMMUNICATE OUR VALUE
Within the next two years, increase community awareness about Cupertino Rotary by 25%.
Identify a form of awareness measurement and develop a baseline
Identify 4-5 key AOS projects and find a way to have the community participate
Identify a professional PR resource to help create key assets (promotion video, pitch deck template, press release template, etc.) and to amp up our SM presence.
Create a “signage policy” for our projects & develop an implementation plan
Get leadership involvement in SM postings to expand our visibility on the what , where, why of our activities

## Slide 5: The Crystalized Goals/Objectives/Initiatives
Member Engagement Facilitation
In the next 5 years, increase member engagement by 5 % each year
Supplement & Enhance current engagement tracking methods to include all club activities for more accurate data
Research and deploy digital methods of capturing data including attendance
During meetings try various options to promote engagement and fellowship
Design and implement a rating tool for real time feedback on events/meetings to effectively promote member engagement

## Slide 6: Next Steps … Starting Rotary Year 23-24
Share the Initiatives with AOS Chairs/Co-Chairs
Request discussion with committees to take ownership
Adoption of goals by an AOS or form a sub-committee
SDO to track activity and progress
Report to Board on an ongoing basis
Share and report to club on a by-annual basis on updates