## Sheet1
| Project Description | 25-26 Budget | 25-26 Actuals | 26-27 Budget | 26-27 Actuals | 25-26 POC | 26-27 POC | Cell Number | Project Start and Location | Project End | # of people needed | Material Items | Comments
1 | Disaster Relief - Venezuela earthquake shelter kits purchased from Rotary | 500 | 0 | 1000 | Approved by the board 7/15 $1000 | Doris & Howard | Val | 4086301844 |  | Done |  |  | Completed. Dan sent a check to Shelterbox on August 20, 2026
2 | Women's Empowerment | 1500 | 1209 | 2000 | 1909 | Gerri Beck | Gerri Beck | 9162128208 | Sept 11, 1590 North A st, Sac. 8am-12:30 | Done | 14 | Food, purses | Completed. $91 under run. Check with Gerri and Dan on the total expenditures. Membership sets up, serves food and clean up. We pay for food and purses. Wear rotary shirt.
3 | Madison Ave Cleanup | 0 | 0 | 0 |  | Neil Shepherd | Neil Shepherd | 9162406736 | Qtrly - Sep 26, 9-10:30 | Done | 10 | Bags, Pickeruppers, Vests, Gloves | Complete. BV High schoolers help. Who is the county waste poc? 4 times a year
4 | Starting Point Soccer Celebration |  |  |  |  | Howard | Howard | 9169567572 | Oct 2, 4:00-6:30 Jackman Middle School, Sac | Done | 5 |  | Complete. Girls teams were celebrated. Membership did set up, clean up, serve food and celebrated with players
5 | OV FO Food Bank food drive |  |  | 400 | 0 |  | Val and Jen |  | Oct 17, 8:30 - 11:30 | Done |  | 26 bags of groceries | Complete. Delivered 26 bags of groceries to the Food Drive on Oct 17.
6 | Safe Halloween |  |  | 400 | * Approx $100 per Bruce | Val | Ree Judge and Bruce Vincent | 9166625411, 8313202856 | Thursday, Oct 29, 3pm-5pm |  |  | Candy,Books, table, table cloth, flyers | Print more flyers to give to pre schoolers. Need candy from members. Posting to FB, Website and Nextdoor (868 views). Check with Ree on expenditures. Ree is getting a fire truck parked by Sangrala and face painting. Posters distributed to village stores and 1,000 flyers to K-3 schools. Northridge, Orangevale Open, Earl LeGette, Twin Lakes, Waldorf and Gold River Discovery school. Doris has books. Need table and table cloth for books.
7 | Xmas Tree Lighting |  |  | 150 |  | Doris | Val | 4086301844 | Dec 3. 5pm-8pm |  | 10 | Table, table cloth, kids projects, candy, flyers | Need sign up sheet. We will be located in the community center where children will perform on the stage and Innerwheel will host a table giving out cookies. $26.90 paid to Parks department for table/chairs and space - email 9.25.26. Kids make Xmas cards with stickers and stamps, 2 tables set up inside building. Sabrina notified that we want to participate on 7/29.
8 | Tree Decorating Contest |  |  | 0 |  | Darlene and Russ Osmonson |  |  | Set up Dec 2, 5pm-6pm and Dec 3, 11am-12pm. |  |  | Tree, decorations | Need sign up sheet. Festival of Trees Dec 3 - 13. Free. Honey Mooners group will set up and take down. Xmas tree and decorations are in the shed. Denis has the key. Sent email to Oxmonson's Oct 23.
9 | Holiday Food Boxes | 3500 | 2561 | 5000 |  | Tom Freeman | Tom Freeman | 5105418919 | Dec 17, ? Time? |  | 20 | Food | Need signup sheet. 110 families at Northridge School. Last year $1000 was donated by the mayor fund. Food donated by the OV FO Food Bank. Does Rotary buy the rest of the food?
10 | Partnership in Education, School Grant Program |  |  | 5000 |  |  | Val |  | 2026-12-01 |  |  |  | 3 applications received to date totaling $1,189 . Sent out reminder email to all schools on Oct 12. Deadline for applications is Oct 23. Applications have been received from Will Rogers School (2), Bella Vista. Email with letter and grant application form went out to 11 school principals and admin asistants on Sept 17. Grant range $250-$1000. Dennis Sarkisian from OV Rotary sent me a detailed email on the Classroom Grants Program. We are duplicating OV's process. Janet Cahill OV Service projects chair. 916-508-6497 OV Rotary phone, orangevalerotaryclub@gmail.com
11 | Bella Vista Basket Ball shirts | 1600 | 717 | 1600 |  | Doris |  |  | 2027-01-01 |  |  | BV purchase warm up shirts for boys & girls and turns in reciepts | I need BV POC from Doris. Board approved going ahead with this project. Diana wants to set up a table for membership drive at girls and boys games. BV hangs large Rotary banner at the game.
12 | Eggstravagansa |  |  | 150 |  | Howard |  | 9169567572 | Mar 27. 9am-12pm |  | 10 | Booiks,Table, popup, table cloth, plants | $50 to parks for space. Cost of plants? Nick Broad does games for kids.
13 | District Grant - 2 Bocci courts for Meristem | 4600 | 5279 | 5000 |  | Nick Broad & Doris | Nick Broad & Doris |  | Spring 2027 |  |  |  | 5K FO + 4K district + 9K meristem = 18K
14 | Big Day of Service | 5000 | 5000 | 5000 |  | Doris | Val |  | May 15, 2027, Casa Robles High School, 9151 Oak Aave, OV | 7:30 | 25 | Popup, Table, table cloth, give a way, flyers | Brad Squires and Angela Lee. Rotary sponsors 2 projects. We donate $5000 to the OV/FO Foundation. Dan Oaks writes the check.
15 | Seinor Lua | 2000 | 1298 | 2000 |  | Doris |  |  | Mid May |  | 15 | Decorations, swag bags | Check with Oakmont to see if they will still pay for food. Jin Cralle has a Oakmont contact. We pay for swag bags. Membership checks in people and serves food. Parks pay for decorations, entertainment, drinks. 100 seniors last year.
16 | Memorial Day Flowers & Cookies | 300 | 250 | 400 |  | Pete Schroeder |  | 9168893209 | May 29. 10am FO Cemetary |  | 5 | Flowers and cookies | Membership provides the cookies. $400 for flower wreath.
17 | 5 Concerts in the Village |  | 900 | 1000 |  | Diana, Doris | Val | 4086301844 | 2027-06-01 |  | 5 | Popup, Table, table cloth, flyers, drawing | Budget is for 2027 concerts. Membership committee also participates.
18 | Food Bank | 0 | 0 |  |  | Doris/ Anne Browning | Lucy Martin/Anne Browning | 9164022142 - Lucy, 9163478704- Anne |  |  | 15 |  | Look into metric for food bank participation. How many cars served per Friday. How many boxes/bags filled of supplies.
19 | Fruit Picking | 150 | 116 | 400 |  | Ryan Palmer | Ryan Palmer | 9168019562 |  |  |  | pole pickers, scale, boxes, bags | Need to purchase scale ~ $200. Set up process to estimate cost of fruit picked. Center Point guys help pick.
20 | Polinator Habitat Kits |  |  | 0 | 0 | Howard |  |  |  |  | 10 |  | Volunteers needed
21 | Honeymooners Club |  |  | 2000 | 0 |  | Russ, Darlene | [5 empty] | Check with Russ/Darlene to find out what this entails.
22 | Innerwheel | 500 | 500 | 500 |  | Doris | Val | [5 empty] | We donate $500 to Innerwheel. Dan Oaks writes the check.
23 | Starting Point (Afgan) | 1000 | 1000 | 1000 |  | Howard |  |  |  |  | 5 |  | $1000 donation to Starting Point. Dan Oaks writes check. Membership delivers Welcome Basket. Starting Point does the baskets.
24 | Center Point | 1000 | 1000 | 1000 |  |  | Val | [5 empty] | $1000 donation. Dan Oaks writes check.
25 | Minstrel Product Drive | [5 empty] | Howard |  |  |  | 15 |  | Procure minstrel items and ask membership to provide. Help assemble boxes.
26 | Habitat for Humanity Sacramento | [5 empty] | Val | [5 empty] | Contact them to see where we can help
27 | Climate Health Now | [5 empty] | Howard | [5 empty] | Donate $ and membership volunteers? Contact Stephanie Holzknecht or Vic Porter to see if we can have them give us a presentation.
28 | Friends of Sailor Bar | [5 empty] | Jen Sims | [5 empty] | Jen is contacting to see if we can do a Big Day of Service Project
29 | Dog Poop Kiosks in FO | [5 empty] | Ryan | [5 empty] | We sponsor some kiosks with post, bag holder, bags and Rotary sign.
30 | CPR Class | [5 empty] | Howard | [5 empty] | Check with membership if they want another class
31 | School of Freedom | [11 empty] | Unplanned event. Non profit. Empowering girls and refugee youth through education and leadership development. Will contact to find out partnering requirements. Email 10/16.
| 2026-27 Allocated Budget |  |  | 34000 | minus 400 not used for food drive | 33600
| Unallocated Funds TBD |  |  | 2775 | plus 400 not used for food drive | 3175
| 2026-2027 Budget |  |  | 36775 |  | 36775
Mark Benvenga - Website
Russ Bechthold - FB