Sustainable Rotary Club Project (SRCP)

Zone 25/26 Activities

Project Coordinator:  PDG Deniel Banks

(e) bankspdx@aol.com    (c) 503-805-6718

ADMINISTRATION  (Develop, Watch & Monitor)       ENCOURAGEMENT       CELEBRATION

Project Goal:

#1 –Sustain membership growth within individual clubs year over year for three years.

Process Goals:

#1 -- Assemble a group of 100-120 clubs from within the Zones 25/26 that are willing to commit to year over year growth in membership for 3 years

#2 – Take a non-prescriptive / organic, flexible, customer service approach

#3 – Determine sustainable processes used by Clubs that can be shared throughout both Zones

#4 – When asked, support Clubs’ efforts on how to grow by building on current successes

Key Points:

- Any size club may participate as long as the club president, PE, club board(s), and relevant other senior leaders agree that they intend their club to grow and will fully commit to all aspects of the Project;

- Participating Clubs will sign a Commitment Letter and designate a club contact person;

- Clubs will agree to and participate in a pre- and post- project assessment (ex. ‘Evaluate Your Brand Experience’ or possibly ‘Health Check’);

- The SRCP Coordinator will do monthly or every other month telephone and/or email check-ins with participating Clubs in order to collect information on membership counts, to discover what is working and what is not, and to encourage continued success;

- The Project is intended to be organic and flexible -- to every extent possible; it will be driven by the participating clubs;

- If requested, the SRCP Coordinator will share successes of other clubs and districts, direct clubs to Membership resources,  and/or share new ideas, etc.;

- Project implementation activities and plan cover the following:  Pre-launch; Launch; On-going Communication; Monitoring and Reporting; Project Evaluation; and Celebration

Why Clubs Might Join the Sustainability Project

Benefits to Clubs for Their Participation

Pride:    Making a significant contribution; seeing ideas implemented.

Competition and a Sense of Involvement:    Having an active role in what is going on.

Recognition:   Being praised for doing a good job.

Perseverance:   Known as a role model for persistence, determination, diligence.

Receiving Approval and Respect of Others:    Receiving the respect of other Clubs; a Club whom others admire and seek out.

Personal Club Achievement:   Feeling good about what the Club is accomplishing.

Exercising Responsibility:  Taking calculated risks; making decisions; feeling accountable.

Creativity:   Having a chance to try out new ideas.

Challenge:     Having to stretch as a Club; taking action to solve problems; coping with change; Being Relevant, Being Relational, Being Ready to grow!

Service Impact:    Feeling needed and being helpful to a Club’s home community and communities around the world.

- A strong Club has stories to tell which attracts new members and keeps current members engaged;

- With more members a Club can increase its Humanitarian Service impact which leads to even more impact and success stories to share;

- More impact and more stories lead to enhanced Public Image’ which in turn helps a Club grow by attracting and keeping more engaged members.

Commit to 3 Rs:  Be Relevant, Be Relational, Be Ready to grow!