## 2020-21
2020-21 District 7430 ACTION PLAN TO GROW ROTARY
|  |  | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | Lead(s) | Team | Start Target Date | Complete Target Date | Comments | Recent Progress | Current Status
|  |  | INCREASE OUR IMPACT | EXPAND OUR REACH | ENHANCE PARTICPANT ENGAGEMENT | INCREASE OUR ABILITY TO ADAPT
GROW MEMBERSHIP
1 | ACTION | Learning & Development program for all club leadership positions (president, secretary, treasurer, membership, public image, foundation) utilizing The Learning Center |  |  |  |  | Doug Cook, Janet Kolepp | Learning & Development Team | 2020-05-01 | Ongoing
2 | ACTION | Learning & Development program for Assistant Governors that includes regular Webinar mentoring |  |  |  |  | Doug Cook, Janet Kolepp | Learning & Development Team | 2020-02-01 | 2021-06-01
3 | ACTION | Expand Quarterly "Welcome to The World of Rotary" new member orientation to be Area specific; utlizing the AGs, Area Foundation Coordinators & Presidents |  |  |  |  | Linda Young, Doug Cook | Learning & Development Team | 2020-08-01 | 2021-05-01
4 | ACTION | Training in Alternative Club Models |  |  |  |  | Janet Kolepp Doug Cook |  | 2020-03-01 | 2020-03-01 | District Leadership Team Training
5 | ACTION | Start 3 new Clubs or Satellites in 2020-2021 and add 50 net new members |  |  |  |  | Gary Volpe | Dave Czarnecki, Herb Klotz, | 2020-07-01 | 2021-06-01
6 | ACTION | Best Practice -Finding Leads > Reaching out> Members > Engagement |  |  |  |  | Gary Volpe | Dave Czarnecki, Herb Klotz,
7 | ACTION | "How" to be a Welcoming Club training |  |  |  |  | Doug Cook, Janet Kolepp |  | 2020-02-01 |  | MAPETS
8 | ACTION | Hold Diversity, Equity & Inclusion Awareness training |  |  |  |  | DTA Stephanie Urchick |  | 2020-04-01 |  | District Training Assembly
GROW GIVING
9 | ACTION | Grow PolioPlus donations to Purple Pinkie Race to Zero to $50,000
10 | ACTION | Continue emphasis on Rotary Direct (+25) and Paul Harris Society Members (100+??) Annual Fund Goal +$25,000
11 | ACTION | Share Foundation Points for Service (Upper Perk)
GROW SERVICE
Youth Service Programs
12 | ACTION | Appoint a Youth Services Chair to champian, coordinate & oversee all Youth Service Activities |  |  |  |  | Janet Kolepp | Darlene Scott & Youth program chairs | 2020-07-01 | 2020-07-01
13 | ACTION | Continue district recognition with Youth Service Award (expand to include Youth Protection compliance)
14 | ACTION | Implement new District Student Protection Policy to all clubs |  |  |  |  | Ron Smith | DEC, Sharon Rittenhouse | 2020-04-01 | 2021-06-01
Community Service
15 | ACTION | Promote District & Global Grants. 35+ clubs involved and all District Grant DDF used |  |  |  |  | Bonnie Eckenrode | District Grant Committee | 2020-03-01 | 2021-06-01
16 | ACTION | Vibrant Club News published monthly highlighting Club Projects, Events & Fundraisers |  |  |  |  | Bill Palmer
17 | ACTION | Develop list of Service Opportunties (not requiring funding)
District Service
18 | ACTION | Expand District Adminstrator role that fully engages the ClubRunner PLATFORM inlcuding website management, event management, member database, communication tools including weekly bulletin |  |  |  |  | Janet Kolepp Sharon Rittenhouse |  | 2020-07-01 | 2021-06-01
19 | ACTION | Clubs don't know "how" to use District |  |  |  |  | DG Janet Challenge to > | Leadership Team
International Service
20 | ACTION | Provide Community Assessment Resources & Mentors
21 | ACTION | Expand International Service trip opportunties (trips and publicize Rotary wide opportunties) |  |  |  |  | Cindy Hornaman
22 | ACTION | Support Shelter Box event expansion to District participation
23 | ACTION | Expand Peace Initiatives
GROW PUBLIC IMAGE
24 | ACTION | Create a Public Image Team that supports and empowers clubs to grow Public Image using multiple media outlets (social, press, videos, websites, community events) while being Rotary Brand Champians | [5 empty] | Valerie Deneen, Amy Sheller, Lou Bottitta, Sharon Rittenhouse, David Akers |  | 2021-06-01
25 | ACTION | Monthly Videos series "My Rotary Story" "Our Club Rotary Story" |  |  |  |  | Janet Kolepp, Amy Sheller |  | 2020-06-01 | 2021-07-01
26 | ACTION | Develop list of Rotary Speakers for club meetings
Clubs don't understand "how" to use the district
AGs Role - Mentor to Club President
Minimize the issue of every year change of leadership
Expectations of leadership / leverage technology

## 2019-20
2019-20 District 7430 ACTION PLAN TO GROW ROTARY (As of Dec 31, 2019)
|  |  | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | Lead(s) | Team | Start Target Date | Complete Target Date | Comments | Recent Progress | Current Status
|  |  | INCREASE OUR IMPACT | EXPAND OUR REACH | ENHANCE PARTICPANT ENGAGEMENT | INCREASE OUR ABILITY TO ADAPT
GROW MEMBERSHIP
| ACTION | Start Succession Planning Best Practice Sharing Program |  |  |  |  | Gwenn Carr, Gary Englehardt |  | 2019-08-01 | 2020-02-01 | Project Completed | Results will be communicated to club leaders in January
| ACTION | Learning & Development program for club leadership positions (president, secretary, treasurer, membership, Public Image/Social media, Foundation) |  |  |  |  | Linda Young, Herb Klotz | Learning & Development Team | 2019-03-01 | 2019-05-01 | Focus with district Training Assembly, online learning | completed for 2019-20
| ACTION | Learning &Development program for Assistant Governors initiated for new AG’s |  |  |  |  | Linda Young, Herb Klotz | Learning & Development Team | 2019-03-01 | 2019-06-01 | April GoToMeeting webinar, MAPETS | completed for 2019-20
| ACTION | Start 3 new clubs in 2019-20 and add 100 net new members |  |  |  |  | Dave Czarnecki | Ron Smith, LenGieseler, Gary Volpe, Cindy Hornaman | 2019-03-01 | 2020-06-01 | New clubs: Montgomeryville, Berks Area 4, Lehigh Valley, Harleysville satellite | 2 new satellite clubs started with plans for 2 more (Lehigh Valley Passport, Chalfont/ Montgomeryville) . Net gain in membership at -8 (Net loss)
| ACTION | Quarterly District level "Welcome to Rotary" new member orientation (move around district) August, Nov, Feb, May |  |  |  |  | Linda Young, Gail Linenberg | Learning & Development Team | 2019-05-01 | 2020-05-01 | Training is well received by new members | Two sessions held. Two sessions planned.
| ACTION | Hold 2 District “Rotary Means Business” Networking Events |  |  |  |  | Dave Czarnecki | Membership Committee | 2019-05-01 |  | Planning Spring Mixer | Area 3 Mixer held October 22
| ACTION | 2020 District Conference focused on making connections & sharing ideas with 400+ attendees |  |  |  |  | Shushma Patel | 2020 District Conference Committee | 2019-03-01 | 2020-04-26 | New committee members welcome | Planning committee meets monthly
GROW SERVICE
Youth Service Programs
| ACTION | Develop & Implement Cross-Communication plan for all District Youth Leadership Programs |  |  |  |  | JoAnne Atwell | Youth Leadership Team | 2019-06-01 |  | Quarterly GoToMeetings scheduled | Next meeting scheduled for early January
| ACTION | Develop & Implement a communication plan with Rotary clubs to grow District Youth Leadership Development Programs |  |  |  |  | Darlene Scott | Youth Leadership Team | 2019-06-01 |  | District Youth Team in ongoing communication | emails on programs sent to presidents & youth leaders
| ACTION | Initiate a district recognition award for Rotary clubs that actively support and promote district youth activities including scholarships |  |  |  |  | Al Engel | Youth Leadership Team | 2019-05-01 | 2019-07-01 | Club Youth Award Developed | Discussed at all DG Visits
Community Service
| ACTION | Promote District & Global Grants. 35+ clubs involved and all District Grant DDF used |  |  |  |  | Bonnie Eckenrode | District Grant Committee | 2019-03-01 | 2020-06-01 | 34 District Grant Projects with 37 clubs plus global
| ACTION | Develop & Implement District Plan to share clubs project opportunities & successes online |  |  |  |  | Cindy Hornaman | International Committee | 2019-08-01 |  | Use District Facebook page & website | international page started with projects listed for intl projects. Local is next on district web-site
International Service
| ACTION | Provide Community Assessment Tools and Training to clubs |  |  |  |  | Cindy Hornaman | International Committee | 2019-05-01 |  | District Training Assembly classes held
Club/District Service
| ACTION | Communication Channels (Optimal Sharing)
| ACTION | Effective Committee Structures
| ACTION | District Leadership Structure & Governance
Vocational Service
ACTION
ACTION
ACTION
GROW GIVING
| ACTION | Grow Polio Plus contributions to Purple Pinkie Race to Zero by 10% to $42,000 |  |  |  |  | John Scott | Purple Pinkie Team | 2019-03-01 | 2019-10-01 | Successful event in October | Over $60,000 raised for Polio Plus
| ACTION | Campaign to get 100 Additional Rotarians using Rotary Direct and 25 Additional Paul Harris Society Members. Annual Fund Goal is $230,000 |  |  |  |  | Bob Hobaugh | Foundation Area Coord., Major Gifts, PHS Lead | 2019-05-01 | 2020-06-01 | Monthly Awareness Campaign underway | As of 12/31/19, we have 29 new Rotary Direct, 17 new PHS members and have raised $96,000 for the annual fund
GROW PUBLIC IMAGE
| ACTION | Establish a District Website working group to ensure that site is optimal for benefitting clubs |  |  |  |  | Cindy Hornaman | Website Task Force (TBD) | 2019-08-01 |  | Consider a college level intern for team | will start with newsletter article for March
| ACTION | Provide training and resources for clubs to use Facebook more effectively to attract new members. |  |  |  |  | David Akers | Public image Team | 2019-05-19 | 2019-11-01 | District Training Assembly, Fall training sessions | Facebook Admin Training on November 16
| ACTION | Focused program to expand Facebook Exposure for clubs and district |  |  |  |  | David Akers | Public image Team | 2019-04-01 |  | District Facebook Program rolled out | 29 clubs participating
| ACTION | Provide People of Action marketing templates to clubs |  |  |  |  | David Akers | Public image Team | 2019-05-01 |  | Will be provided to clubs after Facebook training | Planned for early 2020

## 2021-22
2021-22 District 7430 ACTION PLAN TO GROW ROTARY
Lead(s)
TOGETHER WE SEE A WORLD WHERE PEOPLE UNITE AND TAKE ACTION TO CREATE LASTING CHANGE ACROSS THE GLOBE, IN OUR COMMUNITIES AND IN OURSELVES
|  |  | Committee | Leads | Start Date | End Date |  | Progress Reports
INCREASE OUR IMPACT |  | Effective Problem Solvers
Eradicate Polio
| ACTION | Secure support for Polio Plus in the amount of $50,000 through Purple Pinkie and campaigns | Foundation | J. Scott, H. Klotz, C Ferguson, C Hornaman & B Hobaugh
Increase Humanitarian Projects
| ACTION | Secure support for Annual Fund in the amount of $200,000 | Foundation | C. Hornaman, K. Farrell & B Hobaugh
| ACTION | Add 3 Major Donors and acknowledge all Major Donors | Foundation | M. McCarthy
| ACTION | Add 15 Rotary Direct contributors | Foundation | C. Hornaman
| ACTION | Add 5 Paul Harris Society members | Foundation | C. Hornaman & W. Erdman
Communicate Impact of Service
| ACTION | Advance and follow-up media coverage of non-grant service projects in 15 Clubs | Public Image & Learning | L. Bottitta, B Hobaugh & Assistant Governors
Communicate Impact of Grant Projects
| ACTION | Advance and follow-up media coverage of grant service projects of 15 Clubs | Public Image, Foundation & Internat. Serv | L. Bottitta, H. Klotz, C. Hornaman, B Hobaugh and Assistant Governors
Partner with Government and NGOs
| ACTION | Offer 1 community assessment training for all Clubs | Foundation & Learning | C. Hornaman, B. Hobaugh & Learning Committee
Effective Goal Setting
| ACTION | Quarterly discussion of goal progress for District and semi-annual review by Clubs | Foundation & Learning | C. Hornaman, R. Hobaugh & Learning Committee
| ACTION | Club Central updates in 75% of Clubs | Learning | AGs, B. Hobaugh & Learning Committee
International Service
| ACTION | 2 trainings for Clubs in global projects and Rotary Action Groups | Internat. Service & Learning | C. Hornaman, B. Hobaugh & Learning Committee
EXPAND OUR REACH |  | Activate and Inspire One Another
Grow Membership - Existing Clubs
| ACTION | Increase existing club membership by 70 net 30 | Membership | D. Donaher
Grow Membership - New Clubs
| ACTION | Add 2 new clubs and 2 satellite clubs | Membership | D. Donaher & J. Kolepp
Grow Membership - Education
| ACTION | Train in Club Assessment and Welcoming Clubs for 23 Clubs | Membership, DEI & Learning | D. Donaher, B. Hobaugh, M. Cook, P. Jones, and D. Watson-Bey
| ACTION | Support Diversity, Equity & Inclusion step one training in 13 additional clubs - total 23 | Membership & DEI | D. Donaher, B. Hobaugh & M. Cook, P. Jones, D. Watson-Bey
| ACTION | Training in alternative club models in 1 Training Tuesday and Learning Center for 50% of Clubs | Learning & Membership | B. Hobaugh, D. Donaher & J. Kolepp
| ACTION | Continue Welcome to Rotary programs in quarterly presentations | Welcome to Rotary and Learning | A. Sheller & Learning Committee
| ACTION | Continue Rotary Leadership Institute 1 time for District 7430 and assisting 1 or more other Districts | RLI and Learning | M. Cook and B. Hobaugh
Coordinate Leadership
| ACTION | Setting & monitoring of measurable goals in all action plans | DLT & Clubs | DEC, Chairs, Assistant Governors and Presidents
| ACTION | Train in best practices for Leadership succession | Learning & Membership | G. Carr, G. Engelhardt, B. Hobaugh & Learning Committee
Strengthen Rotary Brand and Image
| ACTION | Training in social media & RI branding for all clubs at 1 Training Tuesday | Public Image & Learning | L. Bottita & V. Deneen
| ACTION | Increase Club participation by 10% to Governor's Public Image Challenge | Public Image | L. Bottita & J. Kolepp
ENHANCE PARTICIPANT ENGAGEMENT |  | Understand the Needs of Others
Learning Center for Rotarians
| ACTION | Complete officer and Rotarian training in Learning Center for 80% of Clubs | Learning | AGs and B. Hobaugh
Learning Center for Rotaractors
| ACTION | Add 2 Rotaract Clubs using Learning Center, Rotaract Handbook and RI materials | Youth and Learning | D. Scott and B. Hobaugh
Learning Center for Interactors
| ACTION | Add 3 Interact Clubs using Learning Center and RI materials | Youth and Learning | D. Scott, Learning Committee and B. Hobaugh
Collaboration Among Participants
| ACTION | Train Clubs in service projects among Rotarians and others | Youth and Learning | D. Scott, B. Hobaugh and Assistant Governors
Educate about Core Values
| ACTION | Showcase Tuesday programs on service, fellowship, diversity, integrity and leadership | Learning and DEI | B. Hobaugh, M. Cook, P. Jones, D. Watson-Bey and Learning Committee
Networking Opportunities
| ACTION | 8 mixers with A. Clubs and B.1. Chambers of Commerce or B.2 Other Non-Rotary Groups | Membership | D. Donaher
Communications from District
| ACTION | Monthly "Welcome Aboard" newsletter | Admin & Learning | B. Hobaugh & Learning Committee
Engaging Youth
| ACTION | Develop a virtual Youth Exchange | Youth and Learning | L. Kennedy and Youth Committee
| ACTION | Develop a STEM Camp for 33 Students in 1st Q 2022-2023 rollout | Youth and STEM | M. Orbin & STEM YEA Committee
| ACTION | Implement an amended Governor's Youth Service Award to reflect current youth projects | Youth and Learning | B. Hobaugh & Youth Committee
| ACTION | Implement new Youth Protection Policy | Youth & Admin | R. Smith YPO
| ACTION | Camp Neidig in person for 100 students | Youth | W. Body & C. Incalcaterra
INCREASE OUR ABILITY TO ADAPT |  | Inventive, Entrepreneurial and Resilient
Service Projects
| ACTION | Develop and promote service projects that are COVID compliant | Foundation & Learning | C. Hornaman & L. Bottitta
Use Virtual Connectivity - Fundraising
| ACTION | Training on virtual & COVID compliant fundraising | Foundation & Learning | C. Hornaman & Innov Cl Adv
Use Virtual Connectivity - Meetings
| ACTION | Training on Zoom practices for in-person, virtual & hybrid meetings | Learning | Selected speakers, D Watson-Bey and B. Hobaugh
Leadership Development
| ACTION | Present on best practices for leadership | Member &Learn | DTA, G Carr & G Englehardt
Regionalization
| ACTION | 25 Rotary Days of Service with multiple Clubs | Membership | D. Donaher, B. Hobaugh& AGs
Communications Among Clubs
| ACTION | Continue "Vibrant Club News" quarterly | Learning & AdminS. Rittenhouse & B. Hobaugh | B. Hobaugh & Learning Committee