## 2019-20
2019-20 District 7430 Strategic Plan (As of September 2019)
Priority | Topic | Goal | Lead(s) | Team | Start Target Date | Complete Target Date | Comments | Recent Progress | Current Status
Unite People | Develop Leaders | Start Succession Planning Best Practice Sharing Program | Gwenn Carr, Gary Englehardt |  | 2019-08-01 | 2020-02-01 | Survey Planned for clubs | Clubs Identified for Study
Unite People | Develop Leaders | Learning & Development program for club leadership positions (president, secretary, treasurer, membership, Public Image/Social media, Foundation) | Linda Young, Herb Klotz | Learning & Development Team | 2019-03-01 | 2019-05-01 | Focus with district Training Assembly, online learning | completed for 2019-20
Unite People | Develop Leaders | Learning &Development program for Assistant Governors initiated for new AG’s | Linda Young, Herb Klotz | Learning & Development Team | 2019-03-01 | 2019-06-01 | April GoToMeeting webinar, MAPETS | completed for 2019-20
Unite People | Grow Membership | Start 3 new clubs in 2019-20 and add 100 net new members | Dave Czarnecki | Ron Smith, LenGieseler, Gary Volpe, Cindy Hornaman | 2019-03-01 | 2020-06-01 | New clubs: Montgomeryville, Berks Area 4, Lehigh Valley, Harleysville satellite | Harleysville satellite chartered, Mixer planned for Mongomeryville, Springfield Twsp Young Prof Satellite Mixer planned
Unite People | Grow Membership | Quarterly District level "Welcome to Rotary" new member orientation (move around district) August, Nov, Feb, May | Linda Young, Gail Linenberg | Learning & Development Team | 2019-05-01 | 2020-05-01 | Roles/Curriculum defined | First session October 7
Unite People | Grow Membership | Provide training and resources for clubs to use Facebook more effectively to attract new members. | David Akers | Public image Team | 2019-05-19 | 2019-11-01 | District Training Assembly, Fall training sessions | Facebook Admin Training on November 16
Unite People | Grow Membership | Hold 2 District “Rotary Means Business” Networking Events | Dave Czarnecki | Membership Committee | 2019-05-01 |  | Initial Mixer in Fall 2019 | Area 3 Mixer October 22
Unite People | Enhance Collaboration | 2020 District Conference focused on making connections & sharing ideas with 400+ attendees | Shushma Patel | 2020 District Conference Committee | 2019-03-01 | 2020-04-26 | New committee members welcome | Planning committee meets monthly
Unite People | Enhance Collaboration | Establish a District Website working group to ensure that site is optimal for benefitting clubs | Cindy Hornaman | Website Task Force (TBD) | 2019-08-01 |  | Consider a college level intern for team | Plan being developed
Unite People | Strengthen Youth Programs | Develop & Implement Cross-Communication plan for all District Youth Leadership Programs | JoAnne Atwell | Youth Leadership Team | 2019-06-01 |  | Quarterly GoToMeetings scheduled | Next meeting scheduled for early December
Unite People | Strengthen Youth Programs | Develop & Implement a communication plan with Rotary clubs to grow District Youth Leadership Development Programs | Darlene Scott | Youth Leadership Team | 2019-06-01 |  | District Youth Team in ongoing communication | emails on programs sent to presidents & youth leaders
Unite People | Strengthen Youth Programs | Initiate a district recognition award for Rotary clubs that actively support and promote district youth activities including scholarships | Al Engel | Youth Leadership Team | 2019-05-01 | 2019-07-01 | Club Youth Award Developed | Discussed at all DG Visits
Take Action | Build Awareness of Rotary | Focused program to expand Facebook Exposure for clubs and district | David Akers | Public image Team | 2019-04-01 |  | District Facebook Program rolled out | 23 clubs participating
Take Action | Build Awareness of Rotary | Provide People of Action marketing templates to clubs | David Akers | Public image Team | 2019-05-01 |  | Will be provided to clubs after Facebook training
Take Action | Increase Local & International Project Impact | Promote District & Global Grants. 35+ clubs involved and all District Grant DDF used | Bonnie Eckenrode | District Grant Committee | 2019-03-01 | 2020-06-01 | 34 District Grant Projects with 37 clubs plus global
Take Action | Increase Local & International Project Impact | Provide Community Assessment Tools and Training to clubs | Cindy Hornaman | International Committee | 2019-05-01 |  | District Training Assembly classes held
Take Action | Increase Local & International Project Impact | Develop & Implement District Plan to share clubs project opportunities & successes online | Cindy Hornaman | International Committee | 2019-08-01 |  | Use District Facebook page & website | Initials plans under development
Take Action | Expand Rotary Foundation Contributions | Grow Polio Plus contributions to Purple Pinkie Race to Zero by 10% to $42,000 | John Scott | Purple Pinkie Team | 2019-03-01 | 2019-10-01 | Planning committee meets bi-monthly | Event Scheduled for October 12, over $35,000 so far
Take Action | Expand Rotary Foundation Contributions | Campaign to get 100 Additional Rotarians using Rotary Direct and 25 Additional Paul Harris Society Members. | Bob Hobaugh | Foundation Area Coord., Major Gifts, PHS Lead | 2019-05-01 | 2020-06-01 | Initial Awareness Campaign underway | Presentations at all DG Visits. Annual fund team plan established

## 2020-21
2020-21 District 7430 Strategic Plan
Priority | Topic | Goal | Lead(s) | Team | Start Target Date | Complete Target Date
Unite People | Develop Leaders
Unite People | Develop Leaders
Unite People | Develop Leaders
Unite People | Grow Membership
Unite People | Grow Membership
Unite People | Grow Membership
Unite People | Grow Membership
Unite People | Enhance Collaboration
Unite People | Enhance Collaboration
Unite People | Strengthen Youth Programs
Unite People | Strengthen Youth Programs
Take Action | Build Awareness of Rotary
Take Action | Build Awareness of Rotary
Take Action | Increase Local & International Project Impact
Take Action | Increase Local & International Project Impact
Take Action | Increase Local & International Project Impact
Take Action | Expand Rotary Foundation Contributions
Take Action | Expand Rotary Foundation Contributions
Take Action | Expand Rotary Foundation Contributions
Internal Operations | Communication Channels (Optimal Sharing)
Internal Operations | Effective Committee Structures
Internal Operations | District Leadership Structure & Governance

## 2021-22
2021-22 District 7430 Strategic Plan
Priority | Topic | Goal | Lead(s) | Team | Start Target Date | Complete Target Date
Unite People | Develop Leaders
Unite People | Develop Leaders
Unite People | Develop Leaders
Unite People | Grow Membership
Unite People | Grow Membership
Unite People | Grow Membership
Unite People | Grow Membership
Unite People | Enhance Collaboration
Unite People | Enhance Collaboration
Unite People | Strengthen Youth Programs
Unite People | Strengthen Youth Programs
Take Action | Build Awareness of Rotary
Take Action | Build Awareness of Rotary
Take Action | Increase Local & International Project Impact
Take Action | Increase Local & International Project Impact
Take Action | Increase Local & International Project Impact
Take Action | Expand Rotary Foundation Contributions
Take Action | Expand Rotary Foundation Contributions
Take Action | Expand Rotary Foundation Contributions
Internal Operations | Communication Channels (Optimal Sharing)
Internal Operations | Effective Committee Structures
Internal Operations | District Leadership Structure & Governance