## 2019-20
2019-20 District 7430 ACTION PLAN TO GROW ROTARY (As of Dec 31, 2019)
|  |  | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | Lead(s) | Team | Start Target Date | Complete Target Date | Comments | Recent Progress | Current Status
|  |  | INCREASE OUR IMPACT | EXPAND OUR REACH | ENHANCE PARTICPANT ENGAGEMENT | INCREASE OUR ABILITY TO ADAPT
GROW MEMBERSHIP
| ACTION | Start Succession Planning Best Practice Sharing Program |  |  |  |  | Gwenn Carr, Gary Englehardt |  | 2019-08-01 | 2020-02-01 | Project Completed | Results will be communicated to club leaders in January
| ACTION | Learning & Development program for club leadership positions (president, secretary, treasurer, membership, Public Image/Social media, Foundation) |  |  |  |  | Linda Young, Herb Klotz | Learning & Development Team | 2019-03-01 | 2019-05-01 | Focus with district Training Assembly, online learning | completed for 2019-20
| ACTION | Learning &Development program for Assistant Governors initiated for new AG’s |  |  |  |  | Linda Young, Herb Klotz | Learning & Development Team | 2019-03-01 | 2019-06-01 | April GoToMeeting webinar, MAPETS | completed for 2019-20
| ACTION | Start 3 new clubs in 2019-20 and add 100 net new members |  |  |  |  | Dave Czarnecki | Ron Smith, LenGieseler, Gary Volpe, Cindy Hornaman | 2019-03-01 | 2020-06-01 | New clubs: Montgomeryville, Berks Area 4, Lehigh Valley, Harleysville satellite | 2 new satellite clubs started with plans for 2 more (Lehigh Valley Passport, Chalfont/ Montgomeryville) . Net gain in membership at -8 (Net loss)
| ACTION | Quarterly District level "Welcome to Rotary" new member orientation (move around district) August, Nov, Feb, May |  |  |  |  | Linda Young, Gail Linenberg | Learning & Development Team | 2019-05-01 | 2020-05-01 | Training is well received by new members | Two sessions held. Two sessions planned.
| ACTION | Hold 2 District “Rotary Means Business” Networking Events |  |  |  |  | Dave Czarnecki | Membership Committee | 2019-05-01 |  | Planning Spring Mixer | Area 3 Mixer held October 22
| ACTION | 2020 District Conference focused on making connections & sharing ideas with 400+ attendees |  |  |  |  | Shushma Patel | 2020 District Conference Committee | 2019-03-01 | 2020-04-26 | New committee members welcome | Planning committee meets monthly
GROW SERVICE
Youth Service Programs
| ACTION | Develop & Implement Cross-Communication plan for all District Youth Leadership Programs |  |  |  |  | JoAnne Atwell | Youth Leadership Team | 2019-06-01 |  | Quarterly GoToMeetings scheduled | Next meeting scheduled for early January
| ACTION | Develop & Implement a communication plan with Rotary clubs to grow District Youth Leadership Development Programs |  |  |  |  | Darlene Scott | Youth Leadership Team | 2019-06-01 |  | District Youth Team in ongoing communication | emails on programs sent to presidents & youth leaders
| ACTION | Initiate a district recognition award for Rotary clubs that actively support and promote district youth activities including scholarships |  |  |  |  | Al Engel | Youth Leadership Team | 2019-05-01 | 2019-07-01 | Club Youth Award Developed | Discussed at all DG Visits
Community Service
| ACTION | Promote District & Global Grants. 35+ clubs involved and all District Grant DDF used |  |  |  |  | Bonnie Eckenrode | District Grant Committee | 2019-03-01 | 2020-06-01 | 34 District Grant Projects with 37 clubs plus global
| ACTION | Develop & Implement District Plan to share clubs project opportunities & successes online |  |  |  |  | Cindy Hornaman | International Committee | 2019-08-01 |  | Use District Facebook page & website | international page started with projects listed for intl projects. Local is next on district web-site
International Service
| ACTION | Provide Community Assessment Tools and Training to clubs |  |  |  |  | Cindy Hornaman | International Committee | 2019-05-01 |  | District Training Assembly classes held
Club/District Service
| ACTION | Communication Channels (Optimal Sharing)
| ACTION | Effective Committee Structures
| ACTION | District Leadership Structure & Governance
Vocational Service
ACTION
ACTION
ACTION
GROW GIVING
| ACTION | Grow Polio Plus contributions to Purple Pinkie Race to Zero by 10% to $42,000 |  |  |  |  | John Scott | Purple Pinkie Team | 2019-03-01 | 2019-10-01 | Successful event in October | Over $60,000 raised for Polio Plus
| ACTION | Campaign to get 100 Additional Rotarians using Rotary Direct and 25 Additional Paul Harris Society Members. Annual Fund Goal is $230,000 |  |  |  |  | Bob Hobaugh | Foundation Area Coord., Major Gifts, PHS Lead | 2019-05-01 | 2020-06-01 | Monthly Awareness Campaign underway | As of 12/31/19, we have 29 new Rotary Direct, 17 new PHS members and have raised $96,000 for the annual fund
GROW PUBLIC IMAGE
| ACTION | Establish a District Website working group to ensure that site is optimal for benefitting clubs |  |  |  |  | Cindy Hornaman | Website Task Force (TBD) | 2019-08-01 |  | Consider a college level intern for team | will start with newsletter article for March
| ACTION | Provide training and resources for clubs to use Facebook more effectively to attract new members. |  |  |  |  | David Akers | Public image Team | 2019-05-19 | 2019-11-01 | District Training Assembly, Fall training sessions | Facebook Admin Training on November 16
| ACTION | Focused program to expand Facebook Exposure for clubs and district |  |  |  |  | David Akers | Public image Team | 2019-04-01 |  | District Facebook Program rolled out | 29 clubs participating
| ACTION | Provide People of Action marketing templates to clubs |  |  |  |  | David Akers | Public image Team | 2019-05-01 |  | Will be provided to clubs after Facebook training | Planned for early 2020

## 2020-21
2020-21 District 7430 ACTION PLAN TO GROW ROTARY
|  |  | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | Lead(s) | Team | Start Target Date | Complete Target Date | Comments | Recent Progress | Current Status
|  |  | INCREASE OUR IMPACT | EXPAND OUR REACH | ENHANCE PARTICPANT ENGAGEMENT | INCREASE OUR ABILITY TO ADAPT
GROW MEMBERSHIP
ACTION
ACTION
ACTION
GROW GIVING
ACTION
ACTION
ACTION
GROW SERVICE
Youth Service Programs
ACTION
ACTION
ACTION
Community Service
ACTION
ACTION
ACTION
Club/District Service
| ACTION | Communication Channels (Optimal Sharing)
| ACTION | Effective Committee Structures
| ACTION | District Leadership Structure & Governance
Vocational Service
ACTION
ACTION
ACTION
International Service
ACTION
ACTION
ACTION
GROW PUBLIC IMAGE
ACTION
ACTION
ACTION

## 2021-22
2021-22 District 7430 ACTION PLAN TO GROW ROTARY
|  | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | RI Strategic Priority | Lead(s) | Team | Start Target Date | Complete Target Date | Comments | Recent Progress | Current Status
|  | INCREASE OUR IMPACT | EXPAND OUR REACH | ENHANCE PARTICPANT ENGAGEMENT | INCREASE OUR ABILITY TO ADAPT
GROW MEMBERSHIP
ACTION
ACTION
ACTION
GROW SERVICE
Youth Service Programs
ACTION
ACTION
ACTION
Community Service
ACTION
ACTION
ACTION
Club/District Service
ACTION
ACTION
ACTION
Vocational Service
ACTION
ACTION
ACTION
International Service
ACTION
ACTION
ACTION
GROW GIVING
ACTION
ACTION
ACTION
GROW PUBLIC IMAGE
ACTION
ACTION
aCTION