## Strategic Plan: Building Rotaract Collaboration

Unite all Rotaract clubs in the district under a functional District Rotaract Committee (DRC) to increase collaboration, training, and impact.

### Assessment & Contact

- Identify all active Rotaract clubs and their presidents. – almost done

- Collect updated contact details and confirm their current activities and needs.

- Will send a welcome email early August introducing the plan to form a DRC and inviting participation.

### Establish the DRC Core Team

- Call for nominations for District Rotaract Representative (DRR) and committee members.

- Set roles: Chair (DRR), Secretary, Events, Membership, Training, and Public Image leads.

- Hold an initial virtual meeting to set expectations.

End August: DRC needs to be formed with defined roles.

### Set Vision & Goals

- Hold a strategy session (online or hybrid) with all Rotaract clubs.

- Agree on shared district goals (e.g., 3 joint projects, leadership training, 10% membership growth).

- Create a shared communication platform (WhatsApp, email group).

September: District-wide goals and communication channels need to be in place.

### Training & Engagement

- Organize a Rotaract Leadership & Skills Workshop for club leaders.

- Share best practices for club growth and project management.

- Launch a monthly DRC newsletter or social post series.

Rotaract DRC organised and lead:  district training session needs to be completed by end September and  ongoing communication started.

### First Collaborative Project

- Plan a district-wide service project (e.g., environmental, youth empowerment, or Polio awareness).

- Assign roles to different clubs for ownership.

- Promote through social media and local Rotary clubs.

Attempt ; First joint project with collaboration /involvement of Rotary clubs.

### Recognition & Motivation

- Launch a Rotaract Awards Program to recognize outstanding clubs and members (growth, impact, creativity).

- Share success stories in district channels and Rotary newsletters.

Launch Rotaract DRC : Awards program and promote.

### Membership Growth Campaign

- Run a "Bring a Friend" Membership Drive across all Rotaract clubs.

- Provide marketing templates and training for club outreach.

Recruitment event: Each club holds one recruitment event.

### Rotary-Rotaract Collaboration

- Pair Rotaract clubs with nearby Rotary clubs for mentorship and joint projects.

- Invite Rotaractors to speak at Rotary meetings.

Encourage: At least one joint meeting or project per club.

### Second District-Wide Event

- Host a Rotaract District Fellowship Day (sports, cultural, or networking event).

- Combine with a leadership or career development session.

Fellowshio event: building district unity.

### Skills & Leadership Development

- Organize a workshop on grants, public speaking, and project funding (with Rotarians as trainers).

- Encourage Rotaractors to take on district-level leadership roles.

Participation: at least 50% club participation.

### Showcase & Publicity

- Collect all clubs’ success stories and projects from the year.

- Publish a District Rotaract Impact Report (digital PDF + social media posts).

- Pitch stories to local press with Rotary support.

### Celebration & Continuity

- Hold a District Rotaract Conference/AGM.

- Elect or confirm next year’s DRC.

- Celebrate successes, recognize leaders, and set next year’s plan.

District conference:  next leadership team in place.

## Key Support Tools

- Monthly Zoom check-ins for club presidents.

- Shared calendar and document drive for events/resources.

- Mentorship connections with Rotarians.

- Recognition (certificates, features, awards) to keep momentum.

Rotaract club guide

## Step-by-Step Guide to Growing Your Rotaract Club and Building Impactful Projects

### 1. Strengthen Your Membership Base

- Make a List of Potential Members: Friends, colleagues, students, young professionals, community leaders.

- Host Social or Interest Events: Informal meet-ups, coffee chats, or a “Discover Rotaract” evening.

- Make It Personal: Invite people personally and explain how Rotaract benefits them (skills, service, networking).

- Follow Up Quickly: After events, welcome interested people and involve them in activities immediately.

### 2. Keep Members Engaged

- Plan Monthly Fun and Service Activities: Balance between social, service, and learning opportunities.

- Give Everyone a Role: Even small roles (e.g., managing a project, handling social media).

- Recognize Contributions: A simple “thank you” or spotlight on social media goes a long way.

### 3. Identify Projects That Matter

- Talk to Your Community: Ask local leaders, schools, or charities about their needs.

- Pick Causes Members Care About: Environment, health, education, youth, etc.

- Start Small: One-day events (e.g., a clean-up, fundraiser, or skills workshop) can grow into bigger projects.

- Check for Impact: Does the project solve a problem, raise awareness, or build skills?

### 4. Collaborate for Bigger Impact

- Work with Your Sponsor Rotary Club: Ask for mentorship, funding tips, or to co-host a project.

- Partner with Other Rotaract or Interact Clubs: Share resources and make events bigger.

- Reach Out to Community Partners: Local businesses, NGOs, or schools may help with sponsorship or volunteers.

- Communicate Clearly: Agree on who does what, and share updates.

### 5. Promote and Celebrate

- Use Social Media Actively: Post event teasers, live updates, and results.

- Celebrate Success: Share impact numbers (people helped, funds raised).

- Thank Everyone: Members, partners, and community supporters.

### 6. Keep Growing

- Ask New Members to Bring a Friend: Growth is easiest through personal invites.

- Create a Welcoming Culture: Make meetings fun, inclusive, and purposeful.

- Review Regularly: Every few months, ask: Are we growing? Are members happy? Are our projects making a difference?